## Slide 1
HOUSE OF ALPHA
Yes Lifers
Go-To-Market Roadmap
April -- September 2026
Prepared for House of Alpha // Confidential

## Slide 2
YES LIFERS GTM
01 / 13
The Thesis
Financial apps have a cold-start problem.
Users arrive skeptical. Enter approximate numbers. Churn before seeing value.
Community inverts this. Members arrive pre-sold, emotionally invested, and ready to engage deeply.
The sequence matters: identity before product, trust before transaction.
Build the tribe. Earn the trust. Hand them the tool.

## Slide 3
YES LIFERS GTM
02 / 13
The Sequence
APR
W1-4
Foundation
Landing page live, 500 quiz completions, message-market fit identified
MAY
W5-8
Community Ignition
200 members, 4 pods active, 40%+ WAU, content engine running
JUN
W9-12
MVP Drop
150 members through snapshot, 70% completion, top 3 UX fixes shipped
JUL-AUG
W13-20
Community Thickens
500 members, Steps 1-3 programmed, full app in final build
SEP
W21-22
Pre-Launch Heat
Beta to pod completers, 15 testimonials captured, press pitched
SEP 15
W23-24
App Launch
1,000 app users, flywheel self-sustaining, advisory pipeline seeded

## Slide 4
YES LIFERS GTM
03 / 13
The Funnel Math
Industry benchmarks applied. Sources: Interact 2026, ScoreApp, Unbounce, Gainsight.
Stage | Volume | Conv. | Benchmark
LinkedIn impressions | 500K | -- | Organic reach, 3-4 posts/week, 12 weeks
Landing page visitors | 10,000 | 2% | LinkedIn organic CTR: 1.5-3.0%
Quiz starts | 4,000 | 40% | Interactive tool engagement vs static
Quiz completions | 2,600 | 65% | Interact 2026: 65% for 5-10 Q quizzes
Email captured | 1,040 | 40.1% | Interact: quiz start-to-lead = 40.1%
Community joins | 500 | 48% | Email-to-community with 4-email drip
Weekly active members | 200 | 40% | Healthy activation: 20-30%, target 40%
App adopters | 175 | 35% | Community-to-product for pre-sold users
Snapshot completed | 122 | 70% | Pre-primed vs 40% cold traffic
Paid plan | 18 | 15% | Freemium-to-paid: 10-20% high-intent
Advisory pipeline | 5 | 4% | High-touch upsell from engaged users

## Slide 5
YES LIFERS GTM
04 / 13
April: Foundation
Weeks 1-4
Action | Owner | KPI
Landing page with Yes Life Score quiz | Tech + Content | 500 quiz completions
A/B test hero messaging (guilt vs aspiration) | Content | Clear winner by W3
Email drip: 4 emails / 10 days, branched by score | Content | 50%+ open rate
Founder origin post on LinkedIn | Founder | 10K+ impressions
Content bank: 20 LI + 15 IG pre-produced | Content | Batch done by W2
Waitlist captures from quiz + landing page | Tech | 300 emails

## Slide 6
YES LIFERS GTM
05 / 13
May: Community Ignition
Weeks 5-8
Action | Owner | KPI
Seed 10-15 HoA advisory clients (pre-briefed) | Founder + Advisory | Active by Day 1
Open to first 100 from waitlist (scarcity) | Community | 100 members by W6
2 rituals: Clarity Circle (Thu) + Say Yes Moment | Community | 40%+ WAU
Launch 4 accountability pods (4-6 each) | Community | 20 pod members
Content: 3 LI + 4 IG/week, alternating CTAs | Content | 500K impressions
Referral: 3 invites = Founding Yes Lifer badge | Tech + Community | 200 links sent

## Slide 7
YES LIFERS GTM
06 / 13
June: MVP Drop
Weeks 9-12
Action | Owner | KPI
MVP (snapshot / Step 1) to community only | Tech | 150 members access
7-day Clarity Challenge: complete + share | Community + Tech | 70% completion
Structured feedback: survey + threads | Community + Tech | Top 3 UX issues
Founder live office hours (recorded) | Founder | Launch content asset
Ship top 3 UX fixes within 2 weeks | Tech | Fixes live by W12
Community share moment on completion | Tech | 50+ shares posted

## Slide 8
YES LIFERS GTM
07 / 13
Jul-Aug: Community Thickens
Weeks 13-20
Action | Owner | KPI
Open Wave 2: quiz >5.0 gets direct invite | Tech + Community | 500 total members
Steps 2-3: Yes Life + Yes Budget (2-wk sprints) | Community + Content | 100 through Steps 1-3
Build full plan: goals, scenarios, Monte Carlo | Tech | App testing by W20
5-10 free Hell Yes! Decision consultations | Advisory | Case studies
App step indicator + share moment integrated | Tech | Flywheel loop live
30%+ content from members (not founders) | Community | Member ratio tracked

## Slide 9
YES LIFERS GTM
08 / 13
Sep: Launch
Weeks 21-24
Action | Owner | KPI
Sep: Announce date. Beta to pod completers. | Founder + Tech | 15 testimonials
Sep: Founding Yes Lifer cutoff. Press outreach. | Community + Content | 3+ press pitches
Sep 15: Community-first launch, personalised onboard | Tech + Community | 600 signups (comm)
Sep W3: Public launch. PH. LinkedIn post. | All | 400 signups (public)
Sep W4: Advisory pipeline from power users | Advisory | 10 conversations
Sep W4: Flywheel assessment. What self-sustains? | All | Retention data

## Slide 10
YES LIFERS GTM
09 / 13
Measurement Framework
PRE-APP (APR-JUN) | Target | Source
Quiz completion rate | 65%+ | Landing page
Quiz-to-email capture | 40%+ | Form analytics
Email open rate (drip) | 50%+ | ESP dashboard
Community WAU | 40%+ | Platform
Pod retention (6-wk) | 75%+ | Manual
LinkedIn engagement | 3%+ | Native analytics
POST-APP (JUL-SEP) | Target | Source
Community-to-app conv. | 35% | Referral tags
Snapshot compl. (community) | 70%+ | MixPanel
Snapshot compl. (cold) | 40%+ | MixPanel
D7 / D30 retention | 60% / 40% | MixPanel cohort
Free-to-paid conversion | 15% | Stripe
Organic referral rate | 30%+ | Referral tracking

## Slide 11
YES LIFERS GTM
10 / 13
Budget Framework (Monthly INR)
Lean community-first GTM. Trades paid acquisition for time and content investment.
Line Item | Range
Community platform (Circle Pro) | 7.5K - 15K
Email / ESP (Beehiiv / ConvertKit) | Free - 5K
Design tools (Canva Pro, Figma) | 3K - 5K
Quiz tooling (Interact / Typeform) | 3K - 5K
Community manager (part-time, from W5) | 25K - 40K
Content creator collabs (2-3/qtr) | 15K - 40K
Paid boost (top organic posts only) | 15K - 35K
Miscellaneous | 5K - 10K
Monthly total | 73.5K - 155K
Comparable paid-acquisition GTM: 5-10L/month in ad spend alone.

## Slide 12
YES LIFERS GTM
11 / 13
Risk Register
Risk | P | Mitigation
Community grows slowly (<100 by W8) | MED | 2-3 micro-influencer partnerships. Viral quiz relaunch.
Engagement drops post-novelty (W8-12) | MED | Pods are key retention lever. Graduate veterans to leadership.
MVP June timeline slips | MED | Scope to snapshot only. No goals engine in MVP.
Cold users churn faster than community | HIGH | Expected. Use churn data to refine community funnel.
Founder bandwidth saturated | HIGH | Community manager by W5. Batch content. Delegate pods by M4.

## Slide 13
YES LIFERS GTM
12 / 13
Decisions Needed
Decision | By | Why
App name confirmation | W1 | Community language and app copy must align from Day 1.
Community platform choice | W1 | Circle (recommended), Geneva, or Slack. Drives cost + onboarding.
Founder content commitment | W1 | Who owns LinkedIn? Origin post, Clarity Circles = 8-10 hrs/wk.
Community manager hire | W4 | Non-negotiable by W5. Without this, quality degrades.
MVP scope lock | W2 | Snapshot only or broader? Determines June feasibility.
Seed member list | W4 | 10-15 HoA clients briefed + committed to post W5-6.
Every member who succeeds becomes the most powerful acquisition channel for the next member.